## Sheet1
Action Item # | Entry date | Original Due date | Planned date of completion | Actual date of completion | Assignee [ -> others to do the same] | Type | Section | Action | Status A=abandoned C=complete H=on hold P=partial | Disposition
124 | 2012-09-10 |  |  |  | Joe Murdock and Ira McDonald | HCD-ATR, Binding |  | Review and update Normative and informative references in IDA Attributes, NAP and TNC Binding specs | P | 11/12/12: Joe will review before next month's Face-to-Face Meeting. Want to get these specs into WG Last call as quickly as possible.
125 | 2012-11-12 |  |  |  | Joe Murdock and Ira McDonald | Log, HCD-Attr, HCD-NAP |  | Send out HCD-Attributes and HCD-NAP Specs for Working Group Final Call once Ira obtains prototyping report.
ITEMS ON HOLD APPEAR BELOW:
33 | 2009-12-10 |  |  |  | Ron Nevo | SHV |  | PWG will contact Symantec (when appropriate) to encourage discussion with the PWG about a SHV. | H | No longer blocked waiting for AI #32 so we can send market rationale to Symantec. Need a volunteer to take over on this task. Ron Nevo will take this task.
34 | 2009-12-10 |  |  |  | Ron Nevo | Remediation |  | PWG will investigate Symantec’s products and their method(s) to “remediate noncompliant endpoints.” Ron Nevo will take over this activity. Randy will pass on his contacts to Ron. | H | Symantec wants an NDA, but PWG cannot do an NDA; will do a generic version; should we invite Symantec to a PWG IDS teleconference? Need a volunteer to take over on this task. Ron nevo will take over this task. Need to indicate to Symantec that we really wdon;t need too much proprietary information from them, but want to give them our information. Can we get Symantec to attend the April meeting in Cupertino?
58 | 2010-06-11 | 2010-08-03 |  |  | Joe Murdock and Ira McDonald | SCCM |  | Create a first draft SCCM binding spec based on the NAP binding spec | H | MS is releasing R3 of SCCM and also a beta of "R-next", while at the same time adding power management; WIMS group may also be interested. On hold due to priorities.
76 | 2011-02-03 |  |  |  | Bill Wagner, Brian Smithson | MPSA |  | Data security article: Bill to draft, Brian to finish | H
COMPLETED ITEMS APPEAR BELOW:
112 | 2011-08-04 |  |  |  | Joe Murdock | IAA |  | add some verbiage to the Security Considerations section about how to handle multiple negotiate security element requests; add security elements to system elements, and security ID to XSSL elements | C
81 | 2011-02-03 |  |  |  | Joe Murdock | IDS-LOG |  | Find the user role definitions in the IA&A or schema documents and import them into the LOG document | C | look at Oauth, OPenId, XACML, SAML, DMTF, IEEE 2600, and the MIBs, for existing role definitions that we can use
124 | 2012-04-27 |  |  |  | Ira McDonald | HCD-ATR |  | Add boilerplate text for multi-valued attributes in IDS Attributes | C | Add statement about attribute grouping
125 | 2012-04-27 |  |  |  | Michael Sweet | IDS-LOG |  | Send prototype experience for PWG Common Log Format | C
116 | 2011-08-25 |  |  |  | Joe Murdock / Ira McDonald | HCD-ATR |  | Create PWG health attributes registry -- and normalize abstract attribute names so they conform with the semantic model | C | accessible in some way -- attribute name, data type, and number to use Joe will convert to plain text and post
118 | 2011-10-06 |  |  |  | Joe Murdock | HCD-ATR |  | Go through the HCD_ATR and HCD_NAP and change the names, data types to the ASN.1 data type names with a mapping table to other data type naming conventions, and codes so that the attributes sort functionally. Update NAP and NEA specification to the latest version Remove attributre code values from HCD Attribute spec. They should only exist on the registry and binding specs | C | Check with Mike on the status of this
123 | 2012-04-12 |  |  |  | Ira McDonald | HCD-TNC |  | Update TNC binding spec to align with the update HCD Attributes values and IETF PT-TLS | C
92 | 2011-04-06 |  |  |  | Michael Sweet | IDS-LOG |  | Update the rational section to higher-level statements (see 4/6/2011 minutes) | C | Check with Mike on the status of this
96 | 2011-05-26 |  |  |  | Joe Murdock | IDS-Model |  | Expand scenarios into use cases for security-related cases | C
122 | 2012-03-15 |  |  |  | Joe Murdock | Charter |  | Update charter for new officers | C | Ask Jessie if he will be co-chair
119 | 2011-10-06 |  |  |  | Joe Murdock | IAA |  | Update the security schema to match the latest PWG authentication type | C
117 | 2011-10-06 |  |  |  | Brian Smithson | 2600 SD |  | provide a review copy of the proposed "terms of reference" to the IDS mailing list | C
120 | 2011-10-06 |  |  |  | Ira McDonald |  |  | Send a note to the SM group about Dublin Core | C
121 | 2011-10-06 |  |  |  | Joe Murdock | admin |  | use Google calendar for IDS meetings | C
107 | 2011-08-04 |  |  |  | Ira McDonald | TNC Binding |  | look at NEA common values wrt PWG defined attributes in NAP | c | Refer to AI 116
109 | 2011-08-04 |  |  |  | Joe Murdock | TNC Binding |  | review how/why we did the HCD_CONFIG_FLAGS wrt supported/not supported mixed in bitmaps | C | Refer to AI 116
115 | 2011-08-04 |  |  |  | Joe Murdock | IAA |  | add document element branch to security ticket | C
114 | 2011-08-04 |  |  |  | Joe Murdock | IAA |  | add Dublin Core to document security ticket | C
113 | 2011-08-04 |  |  |  | Joe Murdock | IAA |  | add a fifth choice "document security" to request security attributes | C
111 | 2011-08-04 |  |  |  | Joe Murdock | IAA |  | change "request elements" to "negotiate elements" | C
110 | 2011-08-04 |  |  |  | Joe Murdock / Ira McDonald | IAA |  | change "attributes" to "elements" | C
108 | 2011-08-04 |  |  |  | Ira McDonald | TNC Binding |  | consider normalizing abstract attribute names so they conform with the semantic model | C | folded into AI #116
106 | 2011-08-04 |  |  |  | Joe Murdock / Ira McDonald | TNC Binding |  | consider IANA registration procedure for PWG health attribute types and how to reference them in PWG specs, and registering new ones for binding-specific ones | C | see AI #116
105 | 2011-08-04 |  |  |  | Brian Smithson | 2600 SD |  | report on ICCC at October F2F | C
104 | 2011-08-04 |  |  | 2011-08-04 | Brian Smithson | 2600 SD |  | post links to join CCVF and CCF | C
103 | 2011-08-04 |  |  | 2011-08-04 | Brian Smithson | 2600 SD |  | post URL for IPA research report on MFP security | C
102 | 2011-08-04 |  |  |  | Joe Murdock | Remediation |  | retire the remediation document from the active list | C
101 | 2011-06-16 |  |  |  | Joe Murdock | HCD-NAP |  | add new NAC attributes to NAP spec (see AI #86) | A | decided not to do this on advice of TNC people
100 | 2011-06-16 |  |  |  | Brian Smithson | WG admin |  | add section to AI list for items on hold | C
99 | 2011-06-16 |  |  |  | All | IDS-LOG |  | Send security-related use cases to Cloud Imaging and IPP WGs | C | request has been made via PWG announce
98 | 2011-05-26 |  |  |  | Brian Smithson | 2600 SD |  | Invite NIAP to June 30 teleconfeence | A | on hold pending go/no-go decision on this project
97 | 2011-05-26 |  |  |  | Brian Smithson | 2600 SD |  | Provide link to NDPP to IDS group and ask for review/comment by 6/16 meeting | C
95 | 2011-05-26 |  |  | 2011-08-04 | Joe Murdock | IDS-IAA |  | Make all of the identification UUIDs in the schema required elements | C | need to merge with symantic model version
94 | 2011-05-12 |  |  |  | Joe Murdock | reqts spec |  | Placement of alerts in the symantic model document | C
93 | 2011-04-06 |  |  |  | Brian Smithson | IDS-LOG |  | Send a message to the list to solicit use cases for the log spec | C
91 | 2011-04-06 |  |  |  | Joe Murdock | WG admin |  | Update the definition of "imaging device" to include projectors and such, not just HCDs | C | updated in charter
90 | 2011-04-06 |  |  |  | Michael Sweet | IDS-LOG |  | Change the title so as to PWG Common Log Format | C
89 | 2011-04-06 |  | 2011-04-28 |  | Brian Smithson | 2600.1 SD |  | Outline ideas/proposals for SD | C
88 | 2011-04-06 |  |  |  | Brian Smithson | 2600.1 SD |  | Post a reminder to the list to read the whitepaper ftp://ftp.pwg.org/pub/pwg/ids/white/2600sd-20110223.pdf | C
87 | 2011-04-06 |  |  |  | Ira McDonald | TNC Binding |  | Inquire with S. Hanna about whether flat binding is appropriate for embedded systems like MFPs, referring to IF-TLV document | C | TNC cannot be a flat binding; Ira will summarize in an email
86 | 2011-04-06 |  |  |  | Ira McDonald | HCD-ATR |  | Inquire with S. Hanna about the importance (or lack) of having attributes for authentication service, log URI, and log enabled | C
85 | 2011-03-24 |  |  |  | Brian Smithson | 2600.1 SD |  | Final review of project charter and send to SC for approval | A | make it initial draft in advance of F2F; will wait until kick-off with NIAP before final review and SC review
84 | 2011-03-10 |  |  |  | Joe Murdock | WG Admin |  | Review IDS Charter to make sure it still reflect new directions. Add discusion as a F2F topic | C | will do at the April F2F
83 | 2011-02-24 |  |  |  | Brian Smithson | 2600.1 SD |  | Propose a schedule for teleconferences with NIAP | C | May 26 F2F, most likely 10-11am
82 | 2011-02-03 |  |  |  | Brian Smithson | 2600.1 SD |  | Revise the charter draft as describe in the Feb F2F minutes | C
80 | 2011-02-03 |  |  |  | Brian Smithson | WG admin |  | Update the description of the IDS WG to include scope that is larger than just NAC/NAP/etc | C
79 | 2011-02-03 |  |  |  | Joe Murdock | Common Reqts |  | Change name from IDS-CR to IDS-REQ | C
78 | 2011-02-03 |  |  |  | Joe Murdock | Log spec |  | Change name from IDS-CLF to IDS-LOG | C
77 | 2011-02-03 |  |  |  | Joe Murdock | NAP Binding |  | Needs a prototype | A | Still…
75 | 2011-01-13 |  |  |  | Joe Murdock Ira mcDonald Bill Wagner | MPSA |  | MPSA Security article | C | Also a WIMS action item
74 | 2010-12-09 |  |  |  | Joe Murdock | security tkt |  | add a digital signature to the security ticket | C
73 | 2010-12-09 |  |  |  | Joe Murdock Ira McDonald Ron Nevo | reqts spec |  | start an IDS common requirements spec to include out-of-scope and terminology sections | C | Base on new PWG template Renamed "IDS model"
72 | 2010-12-09 |  |  |  | Joe Murdock | IA&A |  | direction is not "recommendations only", it is "requirements and recommendations" (pointing to existing standards) because there will be a conformance section | C | Moved to comments for IAA specification
71 | 2010-12-09 |  |  | 2011-01-27 | Joe Murdock | ATR |  | propose by email a multivalued attribute for log location (a URI) to be added to HCD-ATR | C | Posted for discussion at Feb F2F
70 | 2010-12-09 | 2011-01-14 |  |  | Brian Smithson | admin |  | Make arrangements for F2F meeting with NIAP/other schemes at Ricoh SF during RSA week | C
67 | 2010-10-28 |  |  |  | Joe Murdock Ira McDonald | auth |  | Write IDS-Identification-Authentication-and-Authorization-Framework specification | C
69 | 2010-12-02 |  |  |  | Michael Sweet | log format |  | Write HCD Logging specification | C | New draft Feb 2011
68 | 2010-12-02 |  |  |  | Joe Murdock | auth |  | Define IAA Security Ticket (per October 2010 F2F) | C
66 | 2010-10-20 |  |  | 2011-02-02 | Brian Smithson Joe Murdock Ira McDonald | admin |  | Create a project charter for creating IEEE 2600.1 Supporting Documents | C | Posted for discussion at Feb F2F
65 | 2010-10-20 |  |  |  | Joe Murdock Brian Smithson | admin |  | Update the PWG-IDS Charter | C | See AI 66 for Project Charter
64 | 2010-09-30 |  |  |  | Joe Murdock |  |  | Outline an overview of IA&A | C | reviewed at F2F
63 | 2010-08-06 |  |  |  | Bill Wagner | MPSA |  | Add the plan to a new section of the PWG wiki | C | Intro completed but no plan yet and not yet linked to the main page
62 | 2010-08-06 |  |  | 2010-09-29 | Joe Murdock | ATR |  | Add Natural Language to the conformance list in HCD-ATR section 6 | C
61 | 2010-08-06 |  |  | 2010-09-29 | Joe Murdock | ATR and NAP |  | Change the firmware patches list order from reverse to normal in both HCD-ATR and HCD-NAP | C
60 | 2010-06-11 |  |  |  | Joe Murdock | auth |  | First draft of potential resource predicate values (objects, operations, etc.) | C | See AI 67 and 68
59 | 2010-06-11 | 2010-08-03 |  | 2010-08-03 | Michael Sweet | log format |  | Create a first draft of a common logging specification | C
57 | 2010-06-11 |  |  |  | Joe Murdock | ATR and NAP |  | Patch attributes should be array of patches in order they are applied | C
56 | 2010-06-11 |  |  |  | Pete Zehler Ira | Schema |  | Make simple element xxxPatches as a complex type sequence 0~n xxxPatch | C
55 | 2010-06-11 | 2010-08-03 |  |  | Joe Murdock | ATR |  | Add language attribute to ATR | C
54 | 2010-06-11 | 2010-08-03 |  |  | Joe Murdock | NAP |  | Make language attribute required | C
53 | 2010-05-20 | 2010-06-10 |  |  | Joe Murdock |  |  | Write an MPSA newsletter article for publication in November | C | Joe will work with Bill on articles, surveys, etc., to create and maintain a presence with MPSA. Planning to have something to review at the next F2F.
52 | 2010-05-20 | 2010-06-10 | 2010-06-11 |  | all | log format |  | Look at LogFS (http://www.logfs.org) and syslog (http://datatracker.ietf.org/wg/syslog/ and optionally http://www.syslog.org/) | C | we will follow syslog
51 | 2010-04-08 |  |  | 2010-06-05 | Randy Turner | log format |  | compile wishlist for standard log content and format | C
50 | 2010-04-08 | 2010-04-22 |  | 2010-05-18 | Brian Smithson | log format |  | summarize current log standards for 2600.1 | C | posted to ftp ids/white
49 | 2010-04-08 | 2010-04-22 | 2010-06-11 | 2010-06-11 | all | auth |  | look at XACML and geoXACML (www.geoxacml.org) | C
48 | 2010-04-08 | 2010-04-22 |  | 2010-06-09 | Randy Turner | auth |  | post to the IDS list the problem statement about authorization | C
47 | 2010-04-08 | 2010-04-22 | 2010-06-11 |  | all | general |  | Take another look at SCAP and figure out what if anything to do in IDS | A | consider re-opening in Q3 2010
46 | 2010-04-08 | 2010-04-22 |  | 2010-04-22 | Joe Murdock | all docs |  | Change document titles (and page headers, and references to the documents) according to PWG decision to use the acronym and not the entire name “Printer Working Group”. | C | not the NEA doc, since it is going away
45 | 2010-04-08 |  |  |  | Ira McDonald Pete Zehler | Attributes |  | Add HCD attributes to the system object in the MFD semantic model | C
44 | 2010-03-11 |  |  | 2011-08-04 | Ira McDonald | TNC Binding |  | TCG TNC Binding document | C | Make it a TCG/TNC and IETF NEA document, prefering IETF types over TCG.
43 | 2010-02-25 |  |  | 2010-03-11 | Randy Turner | NEA Binding |  | Talk to Steve Hanna about recasting the NEA Binding document as a TCG TNC Binding document | C | Steve said yes
42 | 2010-02-25 |  |  | 2010-04-08 | Joe Murdock Jerry Thrasher Ira McDonald | Attributes |  | add a table of XML data type mapping for the semantic model and some brief normative text suggesting these items should be added to the MFD system object | C
41 | 2010-02-25 |  | 2010-08-03 | 2010-07-30 | Joe Murdock | Remediation |  | look at providing a remediation specification | C | Joe has begun making an actual spec for remediation based on whitepaper
40 | 2010-02-11 | 2010-02-22 |  | 2010-02-22 | Brian Smithson Joe Murdock | agenda |  | add "how to implement remediation" to next meeting agenda | C
39 | 2010-02-11 | 2010-02-25 |  | 2010-02-12 | Joe Murdock | Remediation |  | post remediation document to whitepapers, add date stamp to filename | C
38 | 2010-02-11 |  | 2010-06-10 | 2010-06-07 | Joe Murdock | Binding docs |  | Investigate localization issue | C | Cannot find any information about this in MS documents; Joe will add a localization attribute to the NAP binding spec
37 | 2010-02-11 |  |  |  | Jerry Thrasher | Attributes |  | Same as AI #36 | C
36 | 2010-01-21 |  |  | 2010-03-10 | Brian Smithson Joe Murdock | NAP Binding |  | In acknowledgments: change Dave Whitehead affiliation to “independent contractor” and Peter Cybuck to Kyocera Mita, and change Ron Bergman’s contact information to be consistent with what appears in IPP 2.0. Check to see if Kevin Sigl is still at HP. | C | according to his linkedin page, Kevin is still at HP
35 | 2009-12-10 |  |  | 2010-04-22 | Joe Murdock | Remediation |  | Joe Murdock will investigate Microsoft’s method(s) of remediation. [Is it accomplished by passing a URL?] | C | Yes it is
32 | 2009-12-10 |  | 2010-04-22 | 2010-04-22 | Joe Murdock | Market research |  | Joe Murdock will to develop a “Market Rationale” document – with help from within Sharp. | C | first draft published; update and post for discussion on 4/22/10
31 | 2009-12-10 |  |  |  | Brian Smithson Joe Murdock | NAP Binding |  | Brian Smithson or Joe Murdock will update the note in Appendix X in the NAP document to indicate that the PWG Secretary will “remove this Section.” | C
30 | 2009-12-10 |  |  |  | Brian Smithson Joe Murdock | NAP Binding |  | Brian Smithson or Joe Murdock will clean up the NAP document, accepting the Dec 3 modifications, and will distribute an updated revision as Prototype status. | C
29 | 2009-12-10 |  |  |  | Joe Murdock | Market research |  | Joe Murdock will [edit and] post Peter Cybuck’s information about market research. | C | Due to proprietary concerns, specific information cannot be posted.
28 | 2009-11-12 |  |  | 2010-04-08 | Jerry Thrasher | NAP Binding |  | Jerry Thrasher will send a note to Mike Fenelon to find out if/how it is possible to handle multiple SHVs for the same environment, the same device class, and [possibly] the same SMI number (i.e., PWG)? | A | No response from anyone at Microsoft since at least November.
27 | 2009-10-15 |  |  | 2010-02-11 | Joe Murdock | NAP Binding |  | Joe Murdock will add NAP System Health ID to NAP Binding document and determine how to register a PWG system health ID value. | C | it uses the IANA value, so it is in effect already registered
26 | 2009-10-15 |  |  |  | Joe Murdock | SCCM |  | Joe Murdock will follow up with Eran Dvir (Microsoft) about the SCCM issues, questions, and capabilities. [Ref: AI #22] | A
25 | 2009-09-17 |  |  |  | Peter Cybuck | Market research |  | Peter Cybuck will do some market research about whether customers will accept the proposed method of gaining network access via SCCM. | C | Yes, large but unspecified companies are interested.
24 | 2009-08-18 |  |  | 2009-10-15 | Randy Turner | NEA Binding |  | Randy Turner will ask the NEA e-mail list about their assumptions on modeling [sub-]components with regard to MFD subunits. (Why does NEA not address BIOS and/or NICs as components within a PC?) | C | Randy has received two responses. Steve Hanna (NEA Chair) is working on a list of comments on the NEA binding document.
23 | 2009-08-18 |  |  |  | Mike Fenelon | Value Proposition |  | Mike Fenelon will take on the responsibility for creating a “value proposition” document to help justify the reason behind HCD NAP development. Peter Cybuck and Ron Nevo will provide market information as possible. | A | Jane Maliouta has transferred groups and will no longer work on this task. Mike is attempting to find the right person within Microsoft to do the actual work. (subsumed by AI #32)
22 | 2009-08-18 |  |  | 2009-10-15 | Joe Murdock | NAP Binding |  | Joe Murdock will examine the possible mapping of HCD attributes to SCCM and evaluate the resulting “HCD health assessment” benefit. [This should also result in a list of deficiencies and recommended extensions to be suggested to the MS NAP team.] | C | Proposed mapping spreadsheet was distributed. Questions have been sent to Microsoft.
21 | 2009-08-06 |  |  | 2009-08-18 | Joe Murdock | NAP Binding |  | Joe Murdock will update the NAP Binding specification to address the comments from the June face-to-face meeting and post for review. | C
20 | 2009-07-09 |  |  | 2009-09-17 | Randy Turner |  |  | Randy Turner will post a link to the RSA discussion of TPM alternatives. | C
19 | 2009-06-23 |  |  | 2009-08-18 | Ron Nevo |  |  | Ron Nevo will collect all questions for the Microsoft NAP team that are submitted to the IDS reflector and will pass them along to Microsoft. | C
18 | 2009-06-23 |  |  | 2009-08-06 | Brian Smithson, Joe Murdock | NAP Binding |  | Brian Smithson and/or Joe Murdock will include the attributes that were added to the latest Attribute specification in the next version of the NAP Binding document. | C
17 | 2009-06-23 |  |  | 2009-08-18 | Joe Murdock |  |  | Joe Murdock will send an e-mail to one of the NAP team members asking his opinion on the use of an opaque value for HCD Certification State—and specifically the topic of using vendor-specific plug-ins. | C
16 | 2009-06-04 |  |  | 2009-06-18 | Jerry Thrasher | F2F |  | Jerry Thrasher will add the topic of including IDS information in the MFD Semantic Model to the June Plenary meeting. | C
15 | 2009-06-04 |  |  | 2009-06-23 | Jerry Thrasher | Attributes |  | Jerry Thrasher will create yet another draft of the Attribute document to include corrections identified at the June 4 teleconference. | C
14 | 2009-05-21 |  |  | 2009-06-04 | Brian Smithson | TCG |  | Brian Smithson will communicate the results of the straw poll to the TCG board member responsible for the TCG HCWG. | C
13 | 2009-04-29 |  |  | 2009-05-21 | Dave Whitehead | Telecon |  | Dave Whitehead will announce the next teleconference. | C
12 | 2009-04-29 |  |  | 2009-07-20 | Mike Fenelon | NAP |  | Mike Fenelon will coordinate the next opportunity for a discussion with the Microsoft NAP team. | C
11 | 2009-04-29 |  |  | 2009-05-21 | Dave Whitehead | NEA |  | Dave Whitehead will send a note to Steve Hanna providing the details of the group’s resolutions to his comments. | C
10 | 2009-04-16 |  |  | 2009-11-12 | Brian Smithson | TCG |  | Brian Smithson will investigate whether a formal relationship document can be created between TCG and PWG. He will find out their position on liaison agreements. | C | TCG Board says we can continue with the existing informal relationship. It will be similar to the relationship held with the IEEE P2600 group. [Status information, but no document access.]
9 | 2009-04-16 |  |  | 2009-04-29 | All | TCG |  | Everyone will review Steve Hanna’s comments [http://www.pwg.org/hypermail/ids/0242.html] and be prepared for discussion at the next face-to-face meeting. | C
8 | 2009-03-26 |  |  | 2009-05-21 | Ron Nevo, Dave Whitehead | Action items |  | Ron and Dave will maintain an Action Item spreadsheet that assigns unique IDs to each Action Item and retains the resolution history. | C
7 | 2009-03-26 |  |  | 2009-05-21 | Dave Whitehead | Attributes Microsoft |  | Dave Whitehead and Randy Turner will compile a set of questions that are intended for Microsoft—and maintain the answers on an ongoing basis for future reference. This list should include the topic of the four SOH attributes: MS-Quarantine-State MS-Machine-Inventory MS-Packet-Info MS-CorrelationId | C
6 | 2009-03-26 |  |  | 2009-03-26 | Randy Turner | NEA |  | Randy Turner will send a link to the updated Attributes document to the NEA WG, and solicit their comments. | C
5 | 2009-03-26 |  |  | 2009-04-16 | Dave Whitehead | NAP |  | Dave Whitehead will attempt to resolve the following issue: Which of the defined transport(s) are required to be supported in order to guarantee a device can attach to the network? MS defines DHCP, 802.1x, IPSec, and VPN and has extended each to add SOH information. So, in an environment where we are attaching wirelessly via 802.1x and receive our IP address from DHCP, what happens if we only support SOH over DHCP (or 802.1x)? Will we attach or fail? | C | This issue has been added to the list of questions to be discussed with the MS NAP team.
4 | 2009-03-26 |  |  | 2009-05-21 | Dave Whitehead | NAP Microsoft |  | Dave Whitehead will coordinate with Randy Turner to generate a proposal to Microsoft on proceeding with obtaining NAP information on what they envision would be the content of a profile—including remediation. Need to identify the appropriate point of contact within Microsoft. | C
3 | 2009-03-26 |  |  | 2009-04-29 | Joe Murdock | NAP |  | Joe Murdock will include sequence diagrams as illustrative examples for the NAP binding document. | C
2 | 2009-04-28 |  | 2009-06-23 | 2009-06-23 | Joe Murdock | NAP |  | Joe Murdock will add NAP protocol information to document and update the conformance section. | C
1 | 2009-04-28 |  |  | 2009-12-03 | Randy Turner | NEA |  | Randy Turner will try to find other contacts that would be willing to work with the PWG to help deploy NEA health assessment. (Juniper, Symantec, Cisco are suggested candidates.) Is someone willing to sit down with the PWG and “have discussions”? | C | Randy says he has spoken to several of these companies, and based on a recent document posting [ftp://ftp.pwg.org/pub/pwg/ids/white/ids-ai.pdf], he feels that this Action Item can be closed. He said that no specific “back door” relationships with any of the companies are necessary. The products that we could work with are already generally available today.
x